## Construction Report
Construction Progress Report — House & Land Co
Generated 26 May 2026 at 14:03 · 106 active jobs
| PRE-CONSTRUCTION | [8 empty] | CONSTRUCTION
FORMA Homes — 21 jobs
Client / Job | Deposit | Contract Prep | Contracts Signed | Prelim Works | Prestart Mtg | Final Plans | Bldg Permit | Quantities | Bookings | Welcome | Earthworks | Footings | Slab | Brickwork | Plate Ht | Roof Frame | Roof Cover | Lockup | Plaster | Tiling | PCI 1 | Handover | Status | Progress
Amrapali Mithunakumar Job #10364 · Lot 555 Lot 555 Peppermint Avenue Yanchep WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Blaire Warner Job #10394 · Lot 373 Lot 373 Magnificent Drive Mandogalup WA 6167 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 8%
Daniel Meloncelli Job #10485 · Lot 1154 Lot 1154 Cobalt Way Karnup WA 6176 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 5.5%
Debra Ogilvie & Donald Ogilvie Job #10346 · Lot 724 Lot 724 Victory Parade Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Ern Liew & Ern Liew Job #10383 · Lot 37 Lot 37 Astwood Grove High Wycombe WA 6057 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 16%
Gina Craven Job #10373 · Lot 196 Lot 196 Botania Park Mariginiup WA 6078 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 15%
Harshkumar Joshi & Priyanka Joshi Job #10421 · Lot 324 Lot 324 Coriander Way Henley Brook WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10.5%
Irene Nicoll Job #10381 · Lot 734 Lot 734 14 Navigation Road Brabham WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 32.5%
James Meaney & Sian Elliott Job #10384 · Lot 216 Lot 216 Verbena Way Mariginiup WA 6078 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10.5%
Jose Grado Nunez Job #10362 · Lot 114 Lot 114 3 Harmony Road Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 23.5%
Josh Artis & Kacie Artis Job #10376 · Lot 2742 Lot 2742 Blanc Street Alkimos WA 6038 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 12.5%
Kaviyarasan Vijayakumar & Sriranjani Kaviyarasan Job #10385 · Lot 304 Lot 304 39 Thermal Parkway Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 45%
Liam Harmer Job #10326 · Lot 306 Lot 306 Thermal Parkway Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 32.5%
Liam Waddington Job #10428 · Lot 346 Lot 346 Coriander Way Henley Brook WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 8%
Matthew Waugh & Tarlia Waugh Job #10382 · Lot 310 Lot 310 Knights Way Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 12.5%
Neha Sharma & Harpreet Sharma Job #10390 · Lot 318 Lot 318 Knights Way Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 23.5%
Saffron Somers & Morgan Staniforth-Smith Job #10351 · Lot 941 Lot 941 19 Soursop Street Upper Swan WA 6069 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 35%
Vannak Paing Job #10342 · Lot 208 Lot 208 Bottlebrush Drive Wanneroo WA 6065 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 26.5%
Yang Zhan Job #10353 · Lot 533 Lot 533 272 Sunrise Boulevard Wellard WA 6170 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 47.5%
Yu-Chien Lo & Hsiang-Yu Liu Job #10391 · Lot 309 Lot 309 5 Knights Way Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 26.5%
Zackery Lee Job #10401 · Lot 946 Lot 946 Nevada Way Karnup WA 6176 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 12.5%
La Vida Homes — 64 jobs
Client / Job | Deposit | Contract Prep | Contracts Signed | Prelim Works | Prestart Mtg | Final Plans | Bldg Permit | Quantities | Bookings | Welcome | Earthworks | Footings | Slab | Brickwork | Plate Ht | Roof Frame | Roof Cover | Lockup | Plaster | Tiling | PCI 1 | Handover | Status | Progress
Abhishek Hemandra Baxi Job #23977 · Lot 516 Lot 516 26 Bailup Loop Coodanup WA 6210 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 50%
Abhishek Hemandra Baxi Job #23680 · Lot 1570 Lot 1570 35 Tambrey Avenue Golden Bay WA 6174 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 50%
Adam Gregory Hutchings Job #23368 · Lot 16 Lot 16 10 Picolit Place Pearsall WA 6065 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 22/01/26 | 16/02/26 | — | — | — | — | Construction | 90%
Ajay Gupta & Meenu Gupta Job #23426 · Lot 1011 Lot 1011 21 Sawntimber Approach Whitby WA 6123 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 50%
Alexander Douglas Hart Job #23743 · Lot 185 Lot 185 29 Moort Way Viveash WA 6056 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Alinta Jodie Dewar Job #23765 · Lot 705 Lot 705 141 Apple Street Upper Swan WA 6069 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Anthony Lee Patrick Latta & Nicola Jessica Hazel L Job #24454 · Lot 1129 Lot 1129 Eminence Grove Karnup WA 6167 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 0%
Arkan Mohammed Arkan Al Hassona Job #23933 · Lot 1028 Lot 1028 3 Coyanarup Parade Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Armanda Jean Carcione Job #24122 · Lot 149 Lot 149 Victoria Street Anketell WA 6167 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Ashalia Jasmine Rangiah Job #23941 · Lot 21 Lot 21 60 Tabourie Way Anketell WA 6167 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Blagitza Nedev Job #24479 · Lot 728 Lot 728 Apron View Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 0%
Caite Emma Mckernan Job #24268 · Lot 290 Lot 290 36 Cirrus Drive Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Cameron John Rendell Job #24043 · Lot 368 Lot 368 Aquamarine Parade Karnup WA 6176 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Carlos Augusto Betancur Salazar & Andrea Tatiana L Job #23482 · Lot 765 Lot 765 5 Delaware Approach Alkimos WA 6038 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Chantelle Elizabeth Gargett & Luqman Javed Sayyed Job #24108 · Lot 326 Lot 326 11 Dynamic Approach Jandakot WA 6164 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Christopher Matthew Divis & Stephanie Argiridakis Job #24125 · Lot 677 Lot 677 Downswing Terrace Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Dama Property Holdings Pty Ltd Atf Dama Wealth Fix Job #24047 · Lot 821 Lot 821 Seabound Crescent Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
David Alexander John Ross & Ashleigh Theresia Pilc Job #24269 · Lot 249 Lot 249 27 Hibiscus Loop Henley Brook WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Debbie Ruth Hessenberger Job #22683 · Lot 170 Lot 170 23 Archipelago Way Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 16/12/25 | 02/02/26 | — | — | — | — | Construction | 100%
Dehan Mario Mathew Job #23942 · Lot 964 Lot 964 24 Soursop Street Upper Swan WA 6069 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Donna Marie Quartley Job #22471 · Lot 2010 Lot 2010 82 Mirabilis Avenue Alkimos WA 6038 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 09/09/25 | 10/10/25 | — | — | — | — | Preconstruction | 100%
Eleisha Ellen Schmidt Job #24116 · Lot 842 Lot 842 Seabound Crescent Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Euwina Julie-Ann Christie Job #22638 · Lot 531 Lot 531 128 Capilano Avenue Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Grace Pio Daniel Mbimbi Job #22697 · Lot 290 Lot 290 Cirrus Drive Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 10%
Gurishar Singh Sidhu Job #23841 · Lot 1941 Lot 1941 14 Akuna Way Golden Bay WA 6174 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 60%
Hamish Jainendra Sharma Job #23894 · Lot 94 Lot 94 Tivoli Way Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 30%
Hollie Elisabeth Ninette Crisp & Aaron James Mcqui Job #22566 · Lot 280 Lot 280 15 Desertpea Road Sinagra WA 6065 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 01/05/26 | 15/05/26 | — | — | — | — | Construction | 90%
Jade Debra Rehmie Job #24540 · Lot 22 Lot 22 Swing Crescent Bullsbrook WA 6084 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 0%
Jake Ryan Prescott & Shaegh Vanessa O'Dwyer Job #23928 · Lot 803 Lot 803 Lightning Street Bullsbrook WA 6084 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Jessica Bartolo Job #24143 · Lot 304 Lot 304 Thermal Parkway Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 20%
Joanne Marie Maskell & Michael Terrence Maskell Job #22565 · Lot 402 Lot 402 20 Sultans Street Eglinton WA 6034 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 10/02/26 | 03/03/26 | — | — | — | — | Construction | 90%
Johan Hendrik De Leeuw & Dominic Ifrieda De Leeuw Job #23495 · Lot 1030 Lot 1030 27 Alwal Street Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Judy Sheahan & Andrew Rory Sheahan Job #22430 · Lot 1360 Lot 1360 10 Defender Way Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 12/01/26 | 06/02/26 | — | — | — | — | Construction | 100%
Karina Lee Kidman & Pavel Longva Job #23983 · Lot 696 Lot 696 5 Lister Road Jindalee WA 6036 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Kate Braddick Tutavaha Job #24046 · Lot 1079 Lot 1079 3 Dryander Street Lakelands WA 6180 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 50%
Kerry Patricia Hickey & Brian Patrick Hickey Job #24300 · Lot 774 Lot 774 Aldgate Street Hilbert WA 6112 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Kevin James Sawyer & Stevie Wymond Sawyer Job #24310 · Lot 855 Lot 855 1 Cliffside Way Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Khadar Basha Mohammed Job #23454 · Lot 514 Lot 514 Crossley Road Midvale WA 6056 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 20%
Larissa Michelle Barnett Job #23643 · Lot 517 Lot 517 24 Bailup Loop Coodanup WA 6210 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Laura Jane Andrew Job #23744 · Lot 648 Lot 648 18 Elvire Grove Golden Bay WA 6174 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 60%
Liam Paul Hunt & Charlotte Stephanie Hunt Job #23839 · Lot 143 Lot 143 Bottlebrush Drive Wanneroo WA 6065 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Mandeep Singh Bedi & Rimpreet Kaur Bedi Job #23826 · Lot 1166 Lot 1166 Aviation Boulevard Brabham WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Mandeep Singh Bedi & Rimpreet Kaur Bedi Job #23838 · Lot 914 Lot 914 23 Impact Grove Yanchep WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Marina Abida Mccarthy Job #24042 · Lot 256 Lot 256 18 Ngangk Road Viveash WA 6056 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Nathan Xie Job #23960 · Lot 286 Lot 286 85 Prismatic Drive Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Niraj Kumar Shrestha Job #24101 · Lot 576 Lot 576 28 Zodiac Street Wellard WA 6170 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Prateek Kohli Job #23943 · Lot 60 Lot 60 13 Perito Street Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
R Suganesh & Divya Do Kalai Selvan Job #23848 · Lot 385 Lot 385 Prismatic Drive Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 10%
Ravi Sharma & Manpreet Kaur Job #23634 · Lot 1313 Lot 1313 Gooseberry Road Upper Swan WA 6069 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 20%
Rhiannon Lydia Pearce Job #24464 · Lot 438 Lot 438 Kerferd Street Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Riley Terri Nagtzaam Job #22583 · Lot 28 Lot 28 34 Affinity Circuit Yanchep WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 06/02/26 | 03/03/26 | — | — | — | — | Construction | 90%
Ryan Hayden Munnik Job #23700 · Lot 806 Lot 806 163 Clementine Boulevard Upper Swan WA 6069 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Samantha Jade Boyd & Richard David William Wilson Job #24298 · Lot 1466 Lot 1466 Hull Way Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
Shanly Patrick O'Connor & Kim O'Connor Job #22707 · Lot 14 Lot 14 20 Apley Grove Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 60%
Shasa Mataiapo Evaroa Job #24515 · Lot 1598 Lot 1598 Oracle Street Two Rocks WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 0%
Sophie Louise Mcintosh Job #23524 · Lot 2 Lot 2 4 Arden Avenue Baldivis WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 08/05/26 | 20/05/26 | — | — | — | — | Construction | 90%
Stephanie Lee Black Job #24076 · Lot 49 Lot 49 10 Westwood Crescent Hammond Park WA 6164 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 40%
Swaran Singh & Shweta Devi Job #22775 · Lot 4024 Lot 4024 6 Stimson Way Byford WA 6122 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 50%
Swaran Singh & Shweta Devi Job #22637 · Lot 4134 Lot 4134 Gidgee Drive Byford WA 6122 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 0%
Tiana Shae Trompp & Jayden David Faulkner Job #22595 · Lot 1032 Lot 1032 9 Tundra Crescent Henley Brook WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 11/03/26 | 07/04/26 | — | — | — | — | Construction | 90%
Timothy Phillip Bonell Job #22786 · Lot 1051 Lot 1051 82 Tigermoth Boulevard Bullsbrook WA 6084 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Cancelled | 10%
Trung Thanh Nguyen Job #24323 · Lot 215 Lot 215 Verbena Way Mariginiup WA 6078 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 0%
Varun Kalia & Parul Thakur Job #23690 · Lot 672 Lot 672 7 Powderbark Avenue Coodanup WA 6210 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 40%
Vignesh Kumar Paramasivam Meenakshisundaram & Indu Job #24018 · Lot 166 Lot 166 Earhart Drive Forrestdale WA 6112 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 10%
New Choice Homes — 21 jobs
Client / Job | Deposit | Contract Prep | Contracts Signed | Prelim Works | Prestart Mtg | Final Plans | Bldg Permit | Quantities | Bookings | Welcome | Earthworks | Footings | Slab | Brickwork | Plate Ht | Roof Frame | Roof Cover | Lockup | Plaster | Tiling | PCI 1 | Handover | Status | Progress
Miss Buckley Job #i25148 · Lot 385 Lot 385 Prismatic Drive BALDIVIS WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 06/01/26 | 06/01/26 | — | — | — | — | Preconstruction | 20%
Miss Sharma Job #i25151 · Lot 1115 Lot 1115 Shackleton Terrace BYFORD WA 622 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Miss Wade Job #i26027 · Lot 778 Lot 778 Lot 778 Aldgate Street HILBERT WA 6112 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Mr & Mrs Jarvis Job #i26033 · Lot 284 Lot 284 Eddy Lane JINDALEE WA 6036 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 25/02/26 | 25/02/26 | — | — | — | — | Preconstruction | 23.5%
Mr & Mrs Leaper Job #i25097 · Lot 29 Lot 29 Albinia Avenue ANKETELL WA 6164 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 47%
Mr & Mrs Singh Job #i25061 · Lot 57 Lot 57 Drakesbrook Avenue RAVENSWOOD WA 6208 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 67%
Mr Daish & Miss Nethersole Job #i25136 · Lot 983 Lot 983 Cotton Road LAKELANDS WA 6180 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 18/12/25 | 18/12/25 | — | — | — | — | Preconstruction | 36.5%
Mr Dhliwayo Job #i26014 · Lot 319 Lot 319 Knights Way BALDIVIS WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 22/04/26 | 22/04/26 | — | — | — | — | Preconstruction | 26.5%
Mr Hamilton & Mr Hsu Job #i25066 · Lot 573 Lot 573 Zodiac Street WELLARD WA 6170 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 55%
Mr Hellawell Job #i26031 · Lot 28 Lot 28 Lot 28 Astwood Grove HIGH WYCOMBE WA 6057 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 08/05/26 | 08/05/26 | — | — | — | — | Preconstruction | 20%
Mr Kelly Job #i25067 · Lot 1074 Lot 1074 Constellation Entrance TWO ROCKS WA 6037 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 60.5%
Mr Khumalo Job #i26028 · Lot 529 Lot 529 Lot 529 Shorncliffe Street YANCHEP WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 20%
Mr Lam & Miss Audino Job #i26047 · Lot 332 Lot 332 Lot 332 Coriander Way HENLEY BROOK WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 16.5%
Mr Penumalli & Mrs Munagala Job #i25071 · Lot 216 Lot 216 Eldridge Circuit RAVENSWOOD WA 6208 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 60.5%
Mr Singh Job #i25142 · Lot 598 Lot 598 Renaissance Drive ALKIMOS WA 6038 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 16/12/25 | 16/12/25 | — | — | — | — | Preconstruction | 27%
Mr Singh & Mrs Kaur Job #i25088 · Lot 1 Lot 1 Arden Avenue BALDIVIS WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Construction | 57%
Mr Tate & Miss Armstrong-Mendonca Job #i26010 · Lot 320 Lot 320 Knights Way BALDIVIS WA 6171 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 22/04/26 | 22/04/26 | — | — | — | — | Preconstruction | 26.5%
Mr Turner Job #i26048 · Lot 425 Lot 425 Lot 425 Kerferd Street YANCHEP WA 6035 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 16.5%
Mr. Anandkumar Mishra & Mrs. Riddhi Mishra Job #i25093 · Lot 1093 Lot 1093 Lot 1093 Aquamarine Park KARNUP WA 6176 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 30%
Mrs & Mr Sayyed Job #i26032 · Lot 2073 Lot 2073 Alverston Boulevard HAYNES WA 6112 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | 27/02/26 | 27/02/26 | — | — | — | — | Preconstruction | 27%
Ms Smith Job #i26039 · Lot 345 Lot 345 Lot 345 Coriander Way HENLEY BROOK WA 6055 | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | — | Preconstruction | 16.5%
Legend: | Completed (portal date) | Forecasted (portal estimate) | CD-based forecast (estimated from contract date)